## Product
ID | Title | Owner | Size | Sprint | Status | As a [user role], I want to [goal], so I can [reason]
1 | set up backlog | L | xs | 1 | Complete | add stories, tasks, show others how to make tasks, upload to github
2 | connect to site | D | s | 1 | Complete | connect to tvmaze.com, get information, store to .json file or database, communicate/document use of database/file
3 | code app | E | m | 1 | Complete | connect to database/file, load information so it's ready for gui, communicate/document use of information
4 | design UI | L | L | 1 | Complete | as a developer I want to get information so I can display information on useable screen
5 | send information | D | m | 2 | In Progress | get information from user to database and return desired values
6 | learn android studio | C | s | 1 | Complete | as a developer, I want to download android studio, explore, and take tutorial, so I can make a good app
7 | design ideas | B | L | 2 | Complete | as a customer, I want to have a visualy appealing to the eye, so I can be visually pleased
8 | Calendar | D | m | 4 | In Progress | as a customer, I want to have a calandar so I can see what's going on in the future
9 | Notifications | E | s | 3 | In Progress | as a customer, I want to have notifications so I will be alerted when shows are on
10 | Make UI elements | C | m | 3 | In Progress | as a developer, I want to have UI elements created so I can use them to make the app look good

## Sprint 1
Product ID | Task | Start hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
1 | create sprint tracker, backlog, and burndown | 2 | 1 | 0 | 0 | 0 | 0 | 1
2 | get tvmaze > json | 6 | 2 | 0 | 3 | 1 | 0 | 0
3 | load json to device | 4 | 0 | 0 | 0 | 4 | 0 | 0
4 | design UI | 4 | 0 | 0 | 0 | 2 | 1 | 1
| Actual Remaining Hours | 16 | 13 | 13 | 10 | 3 | 2 | 0
| Estimated Remaining hours | 16 | 13.3333 | 10.6667 | 8 | 5.3333 | 2.6667 | 0

## Sprint 2
Product ID | Task | Start hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
7 | Design UI Look | 3 | 1 | 1 | 1 | 1 | 0 | 0
4 | Make UI tab design function | 10 | 8 | 8 | 3 | 3 | 3 | 0
6 | Android Studio Tutorial | 4 | 4 | 4 | 4 | 2 | 0 | 0
4 | Favorites | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Actual Remaining Hours | 19 | 15 | 15 | 10 | 8 | 3 | 0
| Estimated Remaining hours | 19 | 15.8333 | 12.6667 | 9.5 | 6.3333 | 3.1667 | 0

## Sprint 3
Product ID | Task | Start hours | S | S | M | T | W | T | F | S | S | M | T | W | T | F
10 | Display search results | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 5 | 2 | 1
10 | Search Activity | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
9 | App background service | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0
10 | Desgin Logo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0
| Actual Remaining Hours | 21 | 21 | 21 | 21 | 21 | 17 | 17 | 16 | 15 | 15 | 14 | 14 | 11 | 4 | 2
| Estimated Remaining hours | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0

## Sprint 4
Product ID | Task | Start hours | S | S | M | T | W | T | F | S | S | M | T | W | T | F
10 | Logo Design Compatability | 4
10 | Productionalize Search Functionality | 2
10 | Favorites | 4
9 | Connect notifications and favorites | 2
8 | Calender | 6
| Actual Remaining Hours | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimated Remaining hours | 18 | 16.7143 | 15.4286 | 14.1429 | 12.8571 | 11.5714 | 10.2857 | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0