## Product
ID | Title | Owner | Size | Sprint | Status | As a [user role], I want to [goal], so I can [reason]
1 | set up backlog | L | xs | 1 | Complete | add stories, tasks, show others how to make tasks, upload to github
2 | connect to site | D | s | 1 | Complete | connect to tvmaze.com, get information, store to .json file or database, communicate/document use of database/file
3 | code app | E | m | 1 | Complete | connect to database/file, load information so it's ready for gui, communicate/document use of information
4 | design UI | L | L | 1 | Complete | get information, display information on useable screen
5 | send information | D | m | 2 | In Progress | get information from user to database and return desired values
6 | learn android studio | C | s | 1 | Complete | download android studio, explore, and take a tutorial
7 | design ideas | B | L | 2 | In Progress | as a customer, I want to have a visualy appealing to the eye, so I can be visually pleased
8 | Calendar |  | m |  | Future | as a customer, I want to have a calandar so I can see what's going on in the future
9 | Notifications |  | xs |  | Future | as a customer, I want to have notifications so I will be alerted when shows are on

## Sprint 1
Product ID | Task | Start hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
1 | create sprint tracker, backlog, and burndown | 2 | 1 | 0 | 0 | 0 | 0 | 1
2 | get tvmaze > json | 6 | 2 | 0 | 3 | 1 | 0 | 0
3 | load json to device | 4 | 0 | 0 | 0 | 4 | 0 | 0
4 | design UI | 4 | 0 | 0 | 0 | 2 | 1 | 1
| Actual Remaining Hours | 16 | 13 | 13 | 10 | 3 | 2 | 0
| Estimated Remaining hours | 16 | 13.3333 | 10.6667 | 8 | 5.3333 | 2.6667 | 0

## Sprint 2
Product ID | Task | Start hours | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Remaining
7 | Design UI Look | 2 | 2 | 0 | 0 | 0 | 1 |  | -1
4 | Make UI design function | 10 | 2 | 0 | 5 | 0 |  |  | 3
5 | Link array to UI | 6 | [6 empty] | 6
6 | Android Studio Tutorial | 4 |  |  |  | 2 | 2 |  | 0
0
0
0
0
| Actual Remaining Hours | 22 | 18 | 18 | 13 | 11 | 8 | 8
| Estimated Remaining hours | 22 | 18.3333 | 14.6667 | 11 | 7.3333 | 3.6667 | 0